## Refs
	Abstract
i	Evaluate the benefits, limitations, uncertainties, and resource implications associated with each software platform under consideration
ii	Evaluate the feasibility of analyzing tagging data independently from the main stock assessment models, a potential strategy to reduce model complexity while maintaining scientific robustness
iii	Identify key analytical features and technical capabilities that future stock assessment platforms should incorporate, such as support for spatial structure, tagging integration,
	and flexibility for multi-species and multi-fleet assessments, to ensure that WCPFC assessments remain scientifically credible, transparent, and adaptable to evolving fishery and management needs

	Project outline (Sec. 2.2)
a	Evaluate features and capabilities that will be important in future tuna assessments
b	Explore fitting models to tuna data using existing software platforms
c	Guide decisions on what kind of new software development will be required
d	Establish collaboration with tRFMOs and research labs to achieve these goals

	Terms of reference
1 (2024)	Review and identify a list of necessary features for software to do tuna stock assessments and identify existing software platforms that have these features or capacity to develop these
2 (2024)	Conduct two workshops with selected experts from other tuna RFMOs and/or with relevant expertise. The first workshop can be remote (prior to SC20) and the second one potentially
	in person (post SC20). The main goal will be to communicate the scoping project, upcoming model explorations, and succession plans for MFCL and Stock Synthesis, to seek advice from
	the scientific community, and to seek collaboration with tRFMOs and various research labs
3 (2024)	Explore the new RTMB programming environment and how it could be used in future tuna assessments. Specifically, how to modularize and organize code in RTMB models, on one hand
	code that is specific to one assessment and on the other hand code that is shared between assessments
4 (2024)	Establish collaboration with NOAA scientists to explore the feasibility of enhancing the tagging module in Stock Synthesis, making it more similar to the tagging module in MFCL
5 (2025)	Provide support to the stock assessment team transitioning the 2025 swordfish assessment from MFCL to Stock Synthesis. Also, coordinate with the 2024/2025 striped marlin
	assessment team to start preparing for the transition of that assessment to Stock Synthesis in 2029
6 (2025)	Compare a variety of software platforms using a simplified single-region WCPO yellowfin tuna dataset. The comparison will evaluate available features, run time speed,
	auxiliary tools, time and skills required to develop and diagnose models, and other characteristics
7 (2025)	Prepare alternative workplans and budget scenarios for the larger implementing (main) project to go beyond scoping. The scoping project will be expected to transition into the main implementing
	project based on the discussions at SC21, budget considerations, and funding availability. It is expected that the work leading up SC21 will inform the implementing workplan options and budget estimations
8 (2025)	Communicate with tuna RFMOs and other research labs to establish which RFMOs and labs are willing and able to commit scientist time to collaborate on specific tasks of the
	scoping project, as well as the upcoming main project
9 (2025)	Communicate with tuna RFMOs and the FIMS project team to evaluate whether joint software development by tuna RFMOs could produce FIMS code modules, with the aim to
	develop future tuna assessment models using FIMS modules

## Report
1	Executive summary				1	Executive summary

2	Introduction				2	Introduction
2.1	The need to migrate to new software				2.1	The need to migrate to new software
2.2	Project outline				2.2	Project outline
2.3	Existing software	new: terms of reference			2.4	Terms of reference
2.4	Ongoing and upcoming software development
		promote existing software to own section			3	Evaluation of existing software
3	Possible tasks for SPC to prioritize				3.1	Stock Synthesis
3.1	Migrate assessments to existing software	promote to software development to own section			3.2	Gadget
3.2	Model exploration using existing software				3.3	Other
3.3	Software development
					4	Evaluation of software in early development
4	Timeline				4.1	FIMS
4.1	Pre-assessment workshop 2024				4.2	DTU Movement Model
4.2	International expert meeting 2024				4.3	Other
4.3	Workshop activities in 2024-2026
4.4	Launching the main project				5	Overview of project activities
					5.1	Reaching out to scientific community
5	Required resources				5.2	Reaching out to tuna RFMOs
5.1	Collaboration with other tRFMOs				5.3	Workshops
5.2	SPC staff positions, consultants				5.4	Model explorations
					5.5	Timeline
6	Acknowledgements
					6	Recommended work streams that would require funding
7	References				6.1	Tuna-specific FIMS modules
					6.2	Spatio-temporal full assessment model
A	Appendices
A.1	Participants in the international expert meeting 2024				3	Possible tasks for SPC to prioritize
A.2	List of project deliverables				3.1	Migrate assessments to existing software
					3.2	Model exploration using existing software
					3.3	Software development

					4	Timeline
					4.1	Pre-assessment workshop 2024
					4.2	International expert meeting 2024
					4.3	Workshop activities in 2024-2026
					4.4	Launching the main project

					5	Required resources
					5.1	Collaboration with other tRFMOs
					5.2	SPC staff positions, consultants

					6	Acknowledgements

					7	References

					A	Appendices
					A.1	Participants in the international expert meeting 2024
					A.2	Single-region yellowfin tuna model as a testbed
					A.3	List of project deliverables